## Check list of tests
ID | Req. ID | Module | Test description | Expected result | Status | Comments
1 |  | Login Page | Entering valid characters in the Email field | The mail field on the login page allows valid characters to be entered | Passed
2 |  | Login Page | Entering invalid characters in the Email field | The mail field on the login page does not allow you to enter invalid characters | Passed
3 |  | Login Page | Checking if a warning appears under the Email field while leaving it empty | Warning below the Email field appears when leaving it empty | Passed
4 |  | Login Page | Entering the specified number of characters (12 characters) in the Password field on the login page | The Password field on the login page allows you to enter a specified number of characters (12 characters) | Passed
5 |  | Login Page | Entering in the Password field on the login page is less than the specified number of characters (less than 12 characters) | If you enter less than the specified number of characters (less than 12 characters) in the Password field on the login page, the field is highlighted and displays a warning | Passed
6 |  | Login Page | Entering in the Password field on the login page is more than the specified number of characters (more than 12 characters) | If you enter more than the specified number of characters (more than 12 characters) in the Password field on the login page, the field is highlighted and displays a warning | Passed
7 |  | Login Page | Checking if a warning appears under the Password field while leaving it empty | A warning appears under the "Password" field when leaving it empty | Passed
8 |  | Login Page | Authorization by clicking on the Login button using the saved mail and password in the system | The button allows authorization only if the entered mail and password are available in the system | Passed
9 |  | Login Page | Authorization by clicking on the Login button using an unsaved mail and password in the system | When you click on the Login button using unsaved mail and password in the system, authorization does not occur | Passed
10 |  | Login Page | Authorization by clicking on the Login button with empty fields of mail and password (or one of them) | The button Login does not allow authorization in an empty login and password field (or one of them) | Passed
11 |  | Login Page | Checking the "Show password" button | When you click on the "Show password" button, the password appears in the field | Passed
12 |  | Register Page | Entering valid characters in the Email field | The mail field on the register page allows valid characters to be entered | Passed
13 |  | Register Page | Entering invalid characters in the Email field | The mail field on the register page does not allow you to enter invalid characters | Passed
14 |  | Register Page | Checking if a warning appears under the Email field while leaving it empty | Warning below the Email field appears when leaving it empty | Passed
15 |  | Register Page | Entering the specified number of characters (12 characters) in the Password field on the register page | The Password field on the register page allows you to enter a specified number of characters (12 characters) | Passed
16 |  | Register Page | Entering in the Password field on the register page is less than the specified number of characters (less than 12 characters) | If you enter less than the specified number of characters (less than 12 characters) in the Password field on the register page, the field is highlighted and displays a warning | Passed
10.1 |  | Register Page | Entering in the Password field on the register page is more than the specified number of characters (more than 12 characters) | If you enter more than the specified number of characters (more than 12 characters) in the Password field on the register page, the field is highlighted and displays a warning | Passed
11 |  | Register Page | Checking if a warning appears under the Password field while leaving it empty | A warning appears under the "Password" field when leaving it empty | Passed
12.3 |  | Register Page | Enter the same password in the Confirm password field as in the Password field | When you enter a password in the Confirm password field that matches the password in the Password field, the warning under the field does not appear that the passwords are not similar | Passed
12.5 |  | Register Page | Entering another password in the Confirm password field that differs from the password in the Password field | If you enter another password in the Confirm password field that differs from the password in the Password field, a warning appears under the field that the passwords are not similar | Passed
13.7 |  | Register Page | Checking the "Show password" button | When you click on the "Show password" button, the password appears in the field | Passed
14.9 |  | Register Page | Registration by pressing the Register button using saved mail in the system | Registration by pressing the Register button using saved mail in the system is not possible, a message appears that such mail is already used in the system. | Passed
16.1 |  | Register Page | Registration by pressing the Register button using unical mail in the system | Registration by pressing the Register button using unical mail in the system is possible | Passed
17.3 |  | Register Page | Entering latin characters in the "Full name" field | The "Full name" field allows entering latin characters | Passed
18.3 |  | Register Page | Entering only spaces in the "Full name" field | The "Full name" field does not allow only spaces | Failed | BR1, BR2
19.3 |  | Register Page | Entering special characters in the Full Name field | The "Full name" field does not allow entering special characters | Failed | BR1, BR2
20 |  | Register Page | Checking the possibility of switching between the Login and Register pages using the button at the bottom of the page | Using the buttons at the bottom of the page, you can switch between the Login and Register pages | Passed
21 |  | Page after registration | Checking the correct display of the page interface after registration | After registering, the page should display a button "Explore flats" and a welcome message "Welcome on board" should appear | Failed | BR7
22 |  | Page after registration | Exit using the "Logout" button | Using the "Logout" button, you can go to the Login page | Failed | BR6
23 |  | Page after login | Going to the main page using the "Explore flats" button after authorization | There is a transition to the main page using the "Explore flats" button after authorization | Passed
|  | Main page | Checking the correctness of the interface display according to the requirements and design layouts | The interface must be displayed according to the requirements and design layouts | Passed
24 |  | Main page | Checking usability after scrolling the feed of apartments | After scrolling up the apartment feed, the search field should remain fixed and not transparent, and should not interfere with viewing the apartment feed. | Failed | BR8
25 |  | Main page | Checking autocomplete in the search field for apartments at the address | After the first character entered, a drop-down box should appear with auto-complete options for the address field | Passed
26 |  | Main page | Checking the correctness of sorting by address | Sorting by address is correct | Failed | BR19
27 |  | Main page | Checking the correct operation of the Details button | Clicking on the Details button should open a map with the address of the selected apartment | Failed | BR12
28 |  | Main page | Checking if the map can be zoomed in or out using the scroll button and the CTRL button | You can zoom in or out on the map using the scroll button and the CTRL button. | Passed
29 |  | Main page | Checking the display of the apartment card in the feed | The apartment card in the feed must contain the address, date and time, description and price per night in dollars | Failed | BR16
30 |  | Main page | Checking the button "+ Add flats" | By clicking on the "+ Add flats" button, a form should open for adding a new apartment card | Passed
31 |  | New card add form | Checking the correct display of the form for adding a new apartment card in accordance with the requirements and layouts | The form for adding a new apartment card meets the requirements and layouts | Passed
32 |  | New card add form | Date and time field validation | You can add the date and time to the corresponding date and time field | Passed
33 |  | New card add form | Address field validation | You can add an address to the corresponding address field | Passed
34 |  | New card add form | Checking the price field per night | You can enter price information in the Price per night field | Passed
35 |  | New card add form | Field check Description | You can enter information about the apartment in the Description field | Passed
36 |  | New card add form | Checking the Publish button | After clicking on the Publish button, the information is saved and the card is added to the feed, and the form closes. | Failed | BR25
37 |  | New card add form | Checking the Cancel button | After clicking the Cancel button, the information is not saved and the card is not added to the feed and the form closes. | Passed
38 |  | Main page | Checking the correctness of displaying links in the url field | Links in the url field should be displayed in the format: /flats?city=name (/flats?city=Berlin); /flats/id_квартиры/?city=name (/flats/4lStfea4wlCgIaLjrTYW, /flats/4lStfea4wlCgIaLjrTYW?city=Berlin). | Failed | BR30

## List of the bugs
ID | Status | Priority | Severity | Bug type | Module | Summary
BR1 | New | indicates the manager | Major | Functional | Register page | There is no validation of the Full Name field for valid characters.
BR2 | New | indicates the manager | Major | UI | Register page | There is no warning under the Full Name field when entering invalid characters
BR3 | New | indicates the manager | Minor | Usability | Login page | There is no checkbox Remember password on the Login page
BR4 | New | indicates the manager | Normal | UI | Page after registration | The avatar circle displays incorrect name initials on the page after registration.
BR5 | New | indicates the manager | Minor | Functional | Main page | On the main page, the sandwich menu is not clickable and does not hide the area with the ribbon of apartments
BR6 | New | indicates the manager | Blocker | Functional | Login page | "Page not found" is displayed after clicking on Logout
BR7 | New | indicates the manager | Blocker | Functional | Page after registration | The window does not have the "Explore flats" button immediately after registration
BR8 | New | indicates the manager | Normal | Usability | Main page | Inconvenient transparent field for finding an apartment
BR9 | New | indicates the manager | Minor | UI | Main page | Magnifier in the apartment search field is not at the end of the field
BR10 | New | indicates the manager | Critical | Usability | Main page | Impossible to enlarge the photo of the apartment
BR11 | New | indicates the manager | Critical | Usability | Main page | No contact information for the owner of the apartment
BR12 | New | indicates the manager | Major | Functional | Main page | By clicking on Details, the sorting in the ribbon of apartments by city is reset
BR13 | New | indicates the manager | Normal | Usability | Main page | No sorting by price per night
BR14 | New | indicates the manager | Normal | Usability | Main page | No sorting by apartment availability date
BR15 | New | indicates the manager | Normal | Usability | Main page | No house numbering on the map
BR16 | New | indicates the manager | Normal | Functional | New card add form | Price per night field accepts negative numbers
BR17 | New | indicates the manager | Normal | UI | New card add form | In the Add flats form, the color of the numbers merges with the color of the selection when a date and time is selected
BR18 | New | indicates the manager | Critical | Functional | Main page | Incorrect display on the map of the address of newly added apartments
BR19 | New | indicates the manager | Major | Functional | Main page | Sorting by city does not display the addresses of newly added apartments in this city
BR20 | New | indicates the manager | Critical | Usability | Main page | No option to edit user profile information
BR21 | New | indicates the manager | Critical | Usability | Main page | Can't delete user profile
BR22 | New | indicates the manager | Critical | Usability | Main page | Unable to edit or delete the card of the added apartment
BR23 | New | indicates the manager | Normal | Functional | New card add form | The apartment card is saved without a description
BR24 | New | indicates the manager | Minor | Usability | Main page | Sandwich menu does not collapse left area with ribbon for easy map view
BR25 | New | indicates the manager | Major | Functional | New card add form | Announcement is saved undated using the Publish button, but does not appear in the feed
BR26 | New | indicates the manager | Normal | Usability | Login page | In the authorization window, the Voypost logo is not clickable and does not refresh the page
BR27 | New | indicates the manager | Blocker | Functional | Main page | The page crashes if you insert a long address twice into the search field
BR28 | New | indicates the manager | Critical | Usability | New card add form | It is not possible to add a photo to the card for adding an apartment
BR29 | New | indicates the manager | Major | UI | Main page | Description field text goes beyond the left side with a ribbon of apartments on the main page
BR30 | New | indicates the manager | Major | Functional | Main page | Links in the url field are displayed in the wrong format

## Bug reports
ID | Status | Priority | Severity | Bug type | Module | Summary | Steps to reproduce | Expected result | Actual result | Environment | Author | Assigned to | Attachments
BR6 | New | indicates the manager | Blocker | Functional | Login page | "Page not found" is displayed after clicking on Logout | 1. Click on the circle avatar with initials. 2. In the drop-down window, click on Logout. | Using the "Logout" button, you can go to the Login page | "Page not found" is displayed instead of the Login page | Laptop Acer, Windows 10, Google Chrome 103.0.5060.134 | Hanna Frantseva | Developer name | https://drive.google.com/file/d/1-GvwU86fU0bkTGH_pVXYqSXilch_79MS/view?usp=sharing
BR7 | New | indicates the manager | Blocker | Functional | Page after registration | The window does not have the "Explore flats" button immediately after registration | 1. Fill in all fields in the Register form 2. Click on the Register button 3. Go to the page after registration | After registering, the page should display a button "Explore flats" and a welcome message "Welcome on board" should appear | After registering, the page does not display a button "Explore flats" | Laptop Acer, Windows 10, Google Chrome 103.0.5060.134 | Hanna Frantseva | Developer name | https://drive.google.com/file/d/1JAeCmTK3kR3szIGVDS4b-jE47DAJJRCP/view?usp=sharing
BR18 | New | indicates the manager | Critical | Functional | Main page | Incorrect display on the map of the address of newly added apartments | 1. Open the form for adding a new apartment card. 2. In the form, fill in all the fields, including the address. 3. Press Publish 4. Find the card on the left side of the main page and click Details | The map should display the specified address correctly. | The map displays the specified address incorrectly | Laptop Acer, Windows 10, Google Chrome 103.0.5060.134 | Hanna Frantseva | Developer name | https://drive.google.com/file/d/1Fl53cGyGhp4bFXiQTUgyC3BVO2avHZJ6/view?usp=sharing
BR27 | New | indicates the manager | Blocker | Functional | Main page | The page crashes if you insert a long address twice into the search field | 1. Open the main page 2. Enter the full long address of the apartment in the apartment search field (for example, 15 Broad Street, Manhattan, New York, NY, USA) 3.Copy the address 4. Put a space 5. Paste the copied address | An error pop-up message should appear that the address is entered incorrectly.Page should not fall. | The page crashes and an error message appears in the console: TypeError: Cannot read properties of undefined (reading 'map') Uncaught TypeError: Cannot read properties of undefined (reading 'map') | Laptop Acer, Windows 10, Google Chrome 103.0.5060.134 | Hanna Frantseva | Developer name | https://drive.google.com/file/d/19oYUT1Kx-3wzzi5f00YtXmZLIDLrR3Ph/view?usp=sharing
BR29 | New | indicates the manager | Major | UI | Main page | Description field text goes beyond the left side with a ribbon of apartments | 1. Open the form for adding a new apartment card. 2. In the form, fill in all the fields, including long description. 3. Press Publish 4.Find the card on the left side of the main page | Description field text does not go beyond the left side with a ribbon of apartments on the main page | The text of the Description field has gone beyond the left side with a ribbon of apartments on the main page | Laptop Acer, Windows 10, Google Chrome 103.0.5060.134 | Hanna Frantseva | Developer name | https://drive.google.com/file/d/1-8LracmP9EOBnjSKvN2k_D8EuFQGT1VM/view?usp=sharing